## All Comments
Design Comment Tracking Log
| Client: |  |  |  |  | UO
| Project: |  |  |  |  | 942 Olive Renovation
Project #:
| Phase: |  |  |  |  | 100%DD
| Review Date: |  |  |  |  | Monday, August 17, 2015
Comment By
| Status "Open" or "Closed" | Fortis | MBA | UO | AAA | RAIN | TYLER | UO Facilities | Comment By (Name) | Date | Workgroup (Civil, Struct, Arch, Mech, Elec, Plumb, FP) | Drawing Sheet # | Spec Section | Rating (A= High, C= Low) | Description of Comment | Action Required By | Action Date | Description of Resolution | Date Resolved
1 | EXAMPLE Open |  | X | [5 empty] | EXAMPLE Sienna Hill | 2015-03-30 | EXAMPLE Arch | EXAMPLE A-111 |  |  | EXAMPLE Are 4" Studs Adequate for Plumbing | EXAMPLE SH |  | EXAMPLE 6" Studs minimum in plumbing chase walls - capture on 100% CD Drawings
2 | OPEN |  |  | X |  |  |  |  | Martina Oxoby | 2015-08-21 | ELEC | E0.1 |  |  | RE Raise/Lower, can the user turn the lights off? Or are you advising that electric lights always be on in these spaces because there is not adequate daylight? | Reyes
3 | OPEN |  |  | X |  |  |  |  | Martina Oxoby | 2015-08-21 | ELEC | E0.1 |  |  | If cost savings, remove dimming from print lab 9A. | Reyes
4 | OPEN |  |  | X |  |  |  |  | Martina Oxoby | 2015-08-21 | ELEC | E0.1 |  |  | I thought we couldn't afford daylighting controls? | Reyes/Fortis
5 | OPEN |  |  | X |  |  |  |  | Martina Oxoby | 2015-08-21 | ELEC | E2.0 |  |  | Flex space 117 - move the track lighting from south wall to east wall where tack surface is, unless can add more tack surface on south wall | Reyes/MBA
6 | OPEN |  |  | X |  |  |  |  | Martina Oxoby | 2015-08-21 | ELEC | E2.0 |  |  | Computer and Print Labs labelled OS, schedule says Vacancy - is it the same piece of equipment? | Reyes
7 | OPEN |  |  | X |  |  |  |  | Martina Oxoby | 2015-08-21 | ELEC | E2.0 |  |  | Phone booths will likely be pieces of furniture, DELETE DA fixtures and extend Fixtures LA south to the dividing wall | Reyes
8 | OPEN |  |  | X |  |  |  |  | Martina Oxoby | 2015-08-21 | ELEC | E2.0 | 50% cut sheets |  | Exterior SA fixtures will require COE exterior review. | City
9 | OPEN |  |  | X |  |  |  |  | Martina Oxoby | 2015-08-22 | ELEC | E3.0 |  |  | ADD power outlets in lobby entry 101 near lounge seating. Is ther e any room under the storefront? | Reyes
10 |  |  |  | X |  |  |  |  | John Arndt | 2015-08-25 | ARCH | A9.1 |  |  | Keep projector in computer lab. Replace screen whiteboard. | Reyes/MBA
11 |  |  |  | X |  |  |  |  | John Arndt | 2015-08-25 | ARCH | A9.1 |  |  | Add whiteboard to polymers shop. | MBA
12 |  |  |  | X |  |  |  |  | John Arndt | 2015-08-25 | ARCH | A9.1 |  |  | Add whiteboard to design studio, ideally any available wall surface. | MBA
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276

## General Comments
# | General Comments | Reviewer
1 | Forsee piping and ductwork conflicts over mechanical rooms due to routing limitations. | Greg Wimmer
2
3
4
5
6
7
8
9
10
11
12
13
14
15